## To-Do Tracker
Intellios UX Audit — Implementation To-Do Tracker
41 pages · 69 components · 124 API routes ¦ 5 P0 · 7 P1 · 8 P2 · 6 P3 · 15 Catalyst adoption items
# | Priority | Wave | Status | Category | Task (Finding) | Recommendation | Key Files | Effort | Owner | Target Date | Notes
P0 — Critical: Blocks core user journeys or causes compliance data misinterpretation
1 | P0 | Wave 1 | Done | Component System | Heading token bypass: ui/heading.tsx hardcodes text-zinc-950 instead of semantic text-text token — affects all 36 pages | Re-export Heading from catalyst/heading.tsx in ui/index.ts. Delete ui/heading.tsx. Catalyst version already uses text-text. | src/components/ui/heading.tsx src/components/ui/index.ts src/components/catalyst/heading.tsx | S |  |  | Session 119 — Wave 1 Foundation
2 | P0 | Wave 1 | Done | Destructive Actions | Agent deprecation (terminal/irreversible) and API key revocation have zero confirmation UI | Adopt Catalyst Dialog for all destructive actions. Add type-to-confirm for terminal states (deprecate, revoke). Create shared ConfirmationDialog wrapper. | src/components/catalyst/dialog.tsx components/registry/lifecycle-controls.tsx src/app/admin/api-keys/page.tsx | S |  |  | Session 119 — Wave 1 Foundation
3 | P0 | Wave 3 | Done | Compliance Evidence | SR 11-7 evidence is a raw JSON download — MRM analysts cannot review inline or generate formatted audit-ready reports | Build Compliance Evidence Viewer with SR 11-7 section navigator, expandable evidence per requirement, and PDF export. Use Catalyst DescriptionList + Table. | src/components/mrm/ src/app/blueprints/[id]/report/page.tsx src/app/api/blueprints/[id]/evidence-package/route.ts | L
4 | P0 | Wave 1 | Done | Lifecycle Gap | Suspended agent status exists in StatusBadge with pulsing animation but has no lifecycle path — no UI to enter, investigate, or exit suspension | Add suspended ↔ approved/draft transitions to lifecycle-controls.tsx. Add suspension detail view showing the triggering runtime violation. | src/components/registry/lifecycle-controls.tsx src/components/registry/status-badge.tsx | M
5 | P0 | Wave 3 | Done | Policy Binding | No way to select which policies apply to a specific agent — all policies evaluate all blueprints with no per-agent override | Add policy-agent binding UI: per-agent policy selection panel in registry detail using Catalyst Checkbox. Add API endpoint for agent-level policy overrides. | src/app/governance/policies/ src/app/registry/[agentId]/page.tsx src/lib/db/ | M
P1 — High: Significantly degrades efficiency or confidence for primary personas
1 | P1 | Wave 1 | Done | Dual Component Library | 11 components duplicated between catalyst/ and ui/; Button imported from two sources across 10 files creating inconsistent behaviour | Consolidate: use Catalyst for Heading, Button, Dialog, Alert, Pagination, Combobox. Use ui/ for FormField, Select, Skeleton, TableToolbar, EmptyState. Remove duplicates. | src/components/catalyst/index.ts src/components/ui/index.ts | M |  |  | Session 119 — Wave 1 Foundation
2 | P1 | Wave 2 | Done | Loading States | 40 of 41 pages lack dedicated loading.tsx skeletons — content flashes on every navigation (layout shift) | Create loading.tsx for 8 priority pages using existing Skeleton + SkeletonList components. Match content layout structure. Use blueprints/[id]/report/loading.tsx as template. | src/app/pipeline/ src/app/registry/ src/app/governance/ src/app/governor/ src/app/compliance/ src/app/audit/ src/app/dashboard/ src/app/monitor/ | M
3 | P1 | Wave 2 | Done | Alert → Root Cause | Policy violation requires 4 clicks and a context switch to reach the editable policy rule — no direct link from violation to policy editor | Add 'Edit Policy' link on each violation card in ValidationReport component. Link directly to /governance/policies/[id]/edit. | src/components/governance/validation-report.tsx | S |  |  | Session 119 — Wave 1 Foundation (completed as W1-07)
4 | P1 | Wave 2 | Done | Client-Side Cache | No React Query / SWR — every navigation re-fetches all data from scratch; no stale-while-revalidate, no deduplication | Introduce React Query. Wrap existing fetch() calls with useQuery hooks. Add stale-while-revalidate for all list pages. | All client component pages (src/app/**/page.tsx) | M
5 | P1 | Wave 2 | Done | Governor Filtering | No agent filtering on governor/compliance views — 50+ agents becomes an unscrollable list with no risk-based grouping | Add Catalyst Combobox as multi-select filter for risk tier, department, and tags on /governor and /compliance pages. | src/app/governor/page.tsx src/app/compliance/page.tsx src/components/catalyst/combobox.tsx | M
6 | P1 | Wave 2 | Done | Audit Export | CSV export limited to current 50-entry page only — compliance audits require exporting full filtered result sets | Implement server-side CSV streaming endpoint for full filtered result export. Add action type and agent ID filters to the audit filter bar. | src/app/audit/page.tsx src/app/api/audit/route.ts | M
7 | P1 | Wave 1 | Done | Token Bypass | Multiple pages use raw Tailwind colors (bg-blue-50, text-blue-700, bg-emerald-50) instead of semantic design tokens | Audit all pages for raw colour classes. Replace with semantic token equivalents from globals.css (e.g. bg-info-subtle, text-success-text). | src/app/governance/page.tsx src/app/pipeline/page.tsx src/app/compliance/page.tsx | S |  |  | Session 119 — Wave 1 Foundation
P2 — Medium: Inconsistency or friction that accumulates over repeated use
1 | P2 | Wave 1 | Done | Governor Sidebar | Governor sidebar hardcodes avatar colour (bg-violet-600), missing active-glow shadow, and wrong accent colour (#a78bfa vs var(--sidebar-accent)) | Align governor-sidebar.tsx with main sidebar tokens: use var(--sidebar-accent), add box-shadow: var(--sidebar-active-glow), use bg-primary for avatar. | src/components/nav/governor-sidebar.tsx | S |  |  | Session 119 — Wave 1 Foundation
2 | P2 | Wave 1 | Done | Missing Error Boundaries | Governor sub-app (7 pages) and admin section (6 pages) have no error.tsx — errors fall through to global handler losing navigation context | Add error.tsx to /governor and /admin route segments using the existing error boundary pattern (see src/app/blueprints/error.tsx). | src/app/governor/ src/app/admin/ | S |  |  | Session 119 — Wave 1 Foundation
3 | P2 | Wave 2 | Done | Empty States | 15+ pages render blank content when data is absent — no empty state component, no contextual CTAs | Adopt Catalyst Alert or existing EmptyState component for all list/table views. Include contextual call-to-action for next step. | src/components/ui/empty-state.tsx All pages with tables/lists | M
4 | P2 | Wave 2 | Done | Form Validation | All validation is submit-triggered only — no on-blur feedback, no character count for constrained fields | Add on-blur validation to FormField component. Add character count display for textarea fields (review rationale, policy descriptions). | src/components/ui/form-field.tsx | S |  |  | Session 119 — Wave 1 Foundation
5 | P2 | Wave 2 | Done | Pagination | Registry fetches all agents at once; 6 admin table pages show all records — Catalyst Pagination component exists but is unused | Implement server-side cursor pagination for registry and admin APIs. Wire up Catalyst Pagination component on all table views. | src/app/registry/page.tsx src/components/catalyst/pagination.tsx src/app/api/registry/route.ts | M
6 | P2 | Wave 2 | Done | Approval History | Multi-step approval chain shows visual progress steps but hides prior reviewers' rationale comments | Expand approval chain visualization in ReviewPanel to show each step's reviewer comment using Catalyst DescriptionList. | src/components/review/review-panel.tsx | S |  |  | Session 119 — Wave 1 Foundation
7 | P2 | Wave 2 | Done | Runtime Policy UX | Simulation disabled for runtime policies with no explanation shown to user; no link from policy form to runtime violations view | Add explanatory callout for disabled simulation (e.g. Catalyst Alert with info variant). Add 'View Runtime Violations' TextLink to policy form footer. | src/components/governance/policy-form.tsx | S |  |  | Session 119 — Wave 1 Foundation
8 | P2 | Wave 2 | Done | Search Coverage | Pipeline, governor, compliance, and all admin table pages have no search or filter capability | Add existing TableToolbar component (src/components/ui/table-toolbar.tsx) to all table-based views. Mirror registry page search/filter patterns. | src/app/pipeline/page.tsx src/app/governor/*.tsx src/app/admin/*.tsx src/components/ui/table-toolbar.tsx | M
P3 — Low: Polish and progressive enhancement
1 | P3 | Wave 3 | Done | Dark Mode | No dark mode implemented despite Catalyst dark: variant classes being available — enterprise SOC/NOC users need it | Add CSS custom property overrides in :root[data-theme='dark'] in globals.css. Add theme toggle component. Leverage existing Catalyst dark: classes. | src/app/globals.css src/app/layout.tsx | L |  |  | Session 126 — @custom-variant dark + html.dark token overrides + ThemeToggle + anti-flash script. Wave 3 36/36 complete.
2 | P3 | Wave 3 | Done | Accessibility | Only 29 ARIA attributes across 345 files — missing skip links, aria-live regions, table scope attributes, and 44px touch targets on custom buttons | Accessibility hardening pass: add skip link to layout.tsx, aria-live for chat/notifications, scope on table headers, replace custom button touch targets with Catalyst Button. | src/app/layout.tsx src/components/ui/button.tsx src/components/ui/table.tsx | M
3 | P3 | Wave 3 | Done | Typography Line Height | Mixed /6, /7, /8 line-heights across heading scale — not aligned to 4px/8px baseline grid | Standardize all type scale line-heights to /6 or /8 increments in Catalyst heading component and any overrides. | src/components/catalyst/heading.tsx src/components/ui/heading.tsx | S |  |  | Session 119 — Wave 1 Foundation
4 | P3 | Wave 3 | Done | Max Width Constraint | No max-width on main content area — ultra-wide monitors (2560px+) cause uncomfortable line lengths in tables and text | Add max-w-screen-2xl mx-auto to main content wrapper in layout.tsx. | src/app/layout.tsx | S |  |  | Session 119 — Wave 1 Foundation
5 | P3 | Wave 3 | Done | Optimistic Updates | No optimistic UI for simple mutations (status toggle, rename, inline edits) — users see loading delay for instant-feeling operations | Implement via React Query's onMutate callback for status changes and inline edits. | All mutation handlers across page components | M |  |  | Session 125 — useMutation + optimistic cache patch in LifecycleControls (blueprints), monitor check-one, workflow transitions
6 | P3 | Wave 3 | Done | Policy Cascade Warning | Deleting a policy shows no impact preview — admins cannot know how many blueprints depend on the policy they are removing | Query dependent blueprint count before confirming deletion. Display count in Catalyst Dialog confirmation: 'This policy is evaluated against N blueprints.' | src/app/governance/policies/[id]/edit/page.tsx src/app/api/governance/policies/[id]/route.ts | S
Catalyst UI Kit Adoption — Consolidation & activation of the 27 available components
1 | P1 | Wave 1 | Done | Catalyst: Dialog | Catalyst Dialog (27 available) unused — 7 destructive actions have no confirmation; Dialog provides accessible focus trap + animations | Import Dialog from @/components/catalyst. Wrap all destructive CTAs: deprecate, revoke, delete, remove-rule. Add type-to-confirm for irreversible actions. | src/components/catalyst/dialog.tsx | S |  |  | Session 119 — Wave 1 Foundation
2 | P1 | Wave 1 | Done | Catalyst: Alert | Catalyst Alert unused — ad-hoc coloured div patterns used for empty states and inline warnings throughout app | Replace div-based info/warning/error patterns with Catalyst Alert (info/warning/error/success variants). | src/components/catalyst/alert.tsx Multiple page files | M
3 | P1 | Wave 2 | Done | Catalyst: Pagination | Catalyst Pagination unused — registry and admin pages show all records at once with no page controls | Wire Catalyst Pagination to server-side paginated registry and admin API endpoints. | src/components/catalyst/pagination.tsx src/app/registry/page.tsx | M
4 | P2 | Wave 2 | Done | Catalyst: Combobox | Catalyst Combobox unused — multi-select filtering needed for risk tiers, tags, departments on governor/compliance views | Use Catalyst Combobox for multi-select agent/tag/risk-tier filters on governor and compliance pages. | src/components/catalyst/combobox.tsx src/app/governor/page.tsx | M
5 | P2 | Wave 2 | Done | Catalyst: Checkbox | Catalyst Checkbox unused — policy-agent binding and bulk review selection need checkboxes | Use Catalyst Checkbox for policy-agent binding selection panel and bulk review approval UI. | src/components/catalyst/checkbox.tsx | S
6 | P2 | Wave 1 | Done | Catalyst: Button consolidation | Button imported from both catalyst/button.tsx (8x) and ui/button.tsx (2x) — inconsistent behaviour and styling | Standardize on Catalyst Button everywhere. Map ui/Button variants: primary→color='indigo', destructive→color='red', secondary→outline, ghost→plain. | src/components/ui/button.tsx All files importing from ui/button | S |  |  | Session 119 — Wave 1 Foundation
7 | P2 | Wave 1 | Done | Catalyst: Badge cleanup | Catalyst Badge (18 colour variants) coexists with ui/Badge (8 semantic variants) — ui/Badge is better aligned to Intellios token system | Keep ui/Badge as the standard (semantic variants match design tokens). Remove catalyst/badge.tsx to eliminate duplication. | src/components/catalyst/badge.tsx src/components/ui/badge.tsx | S
8 | P3 | Wave 1 | Done | Catalyst: Switch deduplication | Both catalyst/switch.tsx and ui/switch.tsx are Headless UI wrappers with identical function | Consolidate: keep ui/switch.tsx (token-aligned styles). Remove catalyst/switch.tsx. | src/components/catalyst/switch.tsx src/components/ui/switch.tsx | S |  |  | Session 119 — Wave 1 Foundation
9 | P3 | Wave 1 | Done | Catalyst: DescriptionList deduplication | Both catalyst/description-list.tsx and ui/description-list.tsx exist — ui/ version is used (2x), Catalyst version is unused | Remove catalyst/description-list.tsx. Keep and use ui/description-list.tsx. | src/components/catalyst/description-list.tsx src/components/ui/description-list.tsx | S |  |  | Session 119 — Wave 1 Foundation
10 | P3 | Wave 1 | Done | Catalyst: Divider deduplication | Both catalyst/divider.tsx and ui/divider.tsx exist — ui/ version is used (2x), Catalyst version is unused | Remove catalyst/divider.tsx. Keep ui/divider.tsx. | src/components/catalyst/divider.tsx src/components/ui/divider.tsx | S |  |  | Session 119 — Wave 1 Foundation

## By Wave
Intellios UX Audit — Sorted by Implementation Wave
Wave 1: Foundation (1–2 wks) · Wave 2: Core UX (2–4 wks) · Wave 3: Governance Excellence (4–6 wks)
Priority | Wave | Status | Category | Task | Recommendation | Key Files | Effort | Notes
Wave 1 — Foundation (1–2 weeks)
P0 | Wave 1 | Done | Component System | Heading token bypass: ui/heading.tsx hardcodes text-zinc-950 instead of semantic text-text token — affects all 36 pages | Re-export Heading from catalyst/heading.tsx in ui/index.ts. Delete ui/heading.tsx. Catalyst version already uses text-text. | src/components/ui/heading.tsx src/components/ui/index.ts src/components/catalyst/heading.tsx | S | Session 119 — Wave 1 Foundation
P0 | Wave 1 | Done | Destructive Actions | Agent deprecation (terminal/irreversible) and API key revocation have zero confirmation UI | Adopt Catalyst Dialog for all destructive actions. Add type-to-confirm for terminal states (deprecate, revoke). Create shared ConfirmationDialog wrapper. | src/components/catalyst/dialog.tsx components/registry/lifecycle-controls.tsx src/app/admin/api-keys/page.tsx | S | Session 119 — Wave 1 Foundation
P0 | Wave 1 | To Do | Lifecycle Gap | Suspended agent status exists in StatusBadge with pulsing animation but has no lifecycle path — no UI to enter, investigate, or exit suspension | Add suspended ↔ approved/draft transitions to lifecycle-controls.tsx. Add suspension detail view showing the triggering runtime violation. | src/components/registry/lifecycle-controls.tsx src/components/registry/status-badge.tsx | M
P1 | Wave 1 | Done | Dual Component Library | 11 components duplicated between catalyst/ and ui/; Button imported from two sources across 10 files creating inconsistent behaviour | Consolidate: use Catalyst for Heading, Button, Dialog, Alert, Pagination, Combobox. Use ui/ for FormField, Select, Skeleton, TableToolbar, EmptyState. Remove duplicates. | src/components/catalyst/index.ts src/components/ui/index.ts | M | Session 119 — Wave 1 Foundation
P1 | Wave 1 | Done | Token Bypass | Multiple pages use raw Tailwind colors (bg-blue-50, text-blue-700, bg-emerald-50) instead of semantic design tokens | Audit all pages for raw colour classes. Replace with semantic token equivalents from globals.css (e.g. bg-info-subtle, text-success-text). | src/app/governance/page.tsx src/app/pipeline/page.tsx src/app/compliance/page.tsx | S | Session 119 — Wave 1 Foundation
P1 | Wave 1 | Done | Catalyst: Dialog | Catalyst Dialog (27 available) unused — 7 destructive actions have no confirmation; Dialog provides accessible focus trap + animations | Import Dialog from @/components/catalyst. Wrap all destructive CTAs: deprecate, revoke, delete, remove-rule. Add type-to-confirm for irreversible actions. | src/components/catalyst/dialog.tsx | S | Session 119 — Wave 1 Foundation
P1 | Wave 1 | To Do | Catalyst: Alert | Catalyst Alert unused — ad-hoc coloured div patterns used for empty states and inline warnings throughout app | Replace div-based info/warning/error patterns with Catalyst Alert (info/warning/error/success variants). | src/components/catalyst/alert.tsx Multiple page files | M
P2 | Wave 1 | Done | Governor Sidebar | Governor sidebar hardcodes avatar colour (bg-violet-600), missing active-glow shadow, and wrong accent colour (#a78bfa vs var(--sidebar-accent)) | Align governor-sidebar.tsx with main sidebar tokens: use var(--sidebar-accent), add box-shadow: var(--sidebar-active-glow), use bg-primary for avatar. | src/components/nav/governor-sidebar.tsx | S | Session 119 — Wave 1 Foundation
P2 | Wave 1 | Done | Missing Error Boundaries | Governor sub-app (7 pages) and admin section (6 pages) have no error.tsx — errors fall through to global handler losing navigation context | Add error.tsx to /governor and /admin route segments using the existing error boundary pattern (see src/app/blueprints/error.tsx). | src/app/governor/ src/app/admin/ | S | Session 119 — Wave 1 Foundation
P2 | Wave 1 | Done | Catalyst: Button consolidation | Button imported from both catalyst/button.tsx (8x) and ui/button.tsx (2x) — inconsistent behaviour and styling | Standardize on Catalyst Button everywhere. Map ui/Button variants: primary→color='indigo', destructive→color='red', secondary→outline, ghost→plain. | src/components/ui/button.tsx All files importing from ui/button | S | Session 119 — Wave 1 Foundation
P2 | Wave 1 | To Do | Catalyst: Badge cleanup | Catalyst Badge (18 colour variants) coexists with ui/Badge (8 semantic variants) — ui/Badge is better aligned to Intellios token system | Keep ui/Badge as the standard (semantic variants match design tokens). Remove catalyst/badge.tsx to eliminate duplication. | src/components/catalyst/badge.tsx src/components/ui/badge.tsx | S
P3 | Wave 1 | Done | Catalyst: Switch deduplication | Both catalyst/switch.tsx and ui/switch.tsx are Headless UI wrappers with identical function | Consolidate: keep ui/switch.tsx (token-aligned styles). Remove catalyst/switch.tsx. | src/components/catalyst/switch.tsx src/components/ui/switch.tsx | S | Session 119 — Wave 1 Foundation
P3 | Wave 1 | Done | Catalyst: DescriptionList deduplication | Both catalyst/description-list.tsx and ui/description-list.tsx exist — ui/ version is used (2x), Catalyst version is unused | Remove catalyst/description-list.tsx. Keep and use ui/description-list.tsx. | src/components/catalyst/description-list.tsx src/components/ui/description-list.tsx | S | Session 119 — Wave 1 Foundation
P3 | Wave 1 | Done | Catalyst: Divider deduplication | Both catalyst/divider.tsx and ui/divider.tsx exist — ui/ version is used (2x), Catalyst version is unused | Remove catalyst/divider.tsx. Keep ui/divider.tsx. | src/components/catalyst/divider.tsx src/components/ui/divider.tsx | S | Session 119 — Wave 1 Foundation
Wave 2 — Core UX (2–4 weeks)
P1 | Wave 2 | Done | Loading States | 40 of 41 pages lack dedicated loading.tsx skeletons — content flashes on every navigation (layout shift) | Create loading.tsx for 8 priority pages using existing Skeleton + SkeletonList components. Match content layout structure. Use blueprints/[id]/report/loading.tsx as template. | src/app/pipeline/ src/app/registry/ src/app/governance/ src/app/governor/ src/app/compliance/ src/app/audit/ src/app/dashboard/ src/app/monitor/ | M
P1 | Wave 2 | Done | Alert → Root Cause | Policy violation requires 4 clicks and a context switch to reach the editable policy rule — no direct link from violation to policy editor | Add 'Edit Policy' link on each violation card in ValidationReport component. Link directly to /governance/policies/[id]/edit. | src/components/governance/validation-report.tsx | S | Session 119 — Wave 1 Foundation
P1 | Wave 2 | To Do | Client-Side Cache | No React Query / SWR — every navigation re-fetches all data from scratch; no stale-while-revalidate, no deduplication | Introduce React Query. Wrap existing fetch() calls with useQuery hooks. Add stale-while-revalidate for all list pages. | All client component pages (src/app/**/page.tsx) | M
P1 | Wave 2 | Done | Governor Filtering | No agent filtering on governor/compliance views — 50+ agents becomes an unscrollable list with no risk-based grouping | Add Catalyst Combobox as multi-select filter for risk tier, department, and tags on /governor and /compliance pages. | src/app/governor/page.tsx src/app/compliance/page.tsx src/components/catalyst/combobox.tsx | M
P1 | Wave 2 | Done | Audit Export | CSV export limited to current 50-entry page only — compliance audits require exporting full filtered result sets | Implement server-side CSV streaming endpoint for full filtered result export. Add action type and agent ID filters to the audit filter bar. | src/app/audit/page.tsx src/app/api/audit/route.ts | M
P1 | Wave 2 | Done | Catalyst: Pagination | Catalyst Pagination unused — registry and admin pages show all records at once with no page controls | Wire Catalyst Pagination to server-side paginated registry and admin API endpoints. | src/components/catalyst/pagination.tsx src/app/registry/page.tsx | M
P2 | Wave 2 | Done | Empty States | 15+ pages render blank content when data is absent — no empty state component, no contextual CTAs | Adopt Catalyst Alert or existing EmptyState component for all list/table views. Include contextual call-to-action for next step. | src/components/ui/empty-state.tsx All pages with tables/lists | M
P2 | Wave 2 | Done | Form Validation | All validation is submit-triggered only — no on-blur feedback, no character count for constrained fields | Add on-blur validation to FormField component. Add character count display for textarea fields (review rationale, policy descriptions). | src/components/ui/form-field.tsx | S | Session 119 — Wave 1 Foundation
P2 | Wave 2 | Done | Pagination | Registry fetches all agents at once; 6 admin table pages show all records — Catalyst Pagination component exists but is unused | Implement server-side cursor pagination for registry and admin APIs. Wire up Catalyst Pagination component on all table views. | src/app/registry/page.tsx src/components/catalyst/pagination.tsx src/app/api/registry/route.ts | M
P2 | Wave 2 | Done | Approval History | Multi-step approval chain shows visual progress steps but hides prior reviewers' rationale comments | Expand approval chain visualization in ReviewPanel to show each step's reviewer comment using Catalyst DescriptionList. | src/components/review/review-panel.tsx | S | Session 119 — Wave 1 Foundation
P2 | Wave 2 | Done | Runtime Policy UX | Simulation disabled for runtime policies with no explanation shown to user; no link from policy form to runtime violations view | Add explanatory callout for disabled simulation (e.g. Catalyst Alert with info variant). Add 'View Runtime Violations' TextLink to policy form footer. | src/components/governance/policy-form.tsx | S | Session 119 — Wave 1 Foundation
P2 | Wave 2 | Done | Search Coverage | Pipeline, governor, compliance, and all admin table pages have no search or filter capability | Add existing TableToolbar component (src/components/ui/table-toolbar.tsx) to all table-based views. Mirror registry page search/filter patterns. | src/app/pipeline/page.tsx src/app/governor/*.tsx src/app/admin/*.tsx src/components/ui/table-toolbar.tsx | M
P2 | Wave 2 | Done | Catalyst: Combobox | Catalyst Combobox unused — multi-select filtering needed for risk tiers, tags, departments on governor/compliance views | Use Catalyst Combobox for multi-select agent/tag/risk-tier filters on governor and compliance pages. | src/components/catalyst/combobox.tsx src/app/governor/page.tsx | M
P2 | Wave 2 | Done | Catalyst: Checkbox | Catalyst Checkbox unused — policy-agent binding and bulk review selection need checkboxes | Use Catalyst Checkbox for policy-agent binding selection panel and bulk review approval UI. | src/components/catalyst/checkbox.tsx | S
Wave 3 — Governance Excellence (4–6 weeks)
P0 | Wave 3 | To Do | Compliance Evidence | SR 11-7 evidence is a raw JSON download — MRM analysts cannot review inline or generate formatted audit-ready reports | Build Compliance Evidence Viewer with SR 11-7 section navigator, expandable evidence per requirement, and PDF export. Use Catalyst DescriptionList + Table. | src/components/mrm/ src/app/blueprints/[id]/report/page.tsx src/app/api/blueprints/[id]/evidence-package/route.ts | L
P0 | Wave 3 | To Do | Policy Binding | No way to select which policies apply to a specific agent — all policies evaluate all blueprints with no per-agent override | Add policy-agent binding UI: per-agent policy selection panel in registry detail using Catalyst Checkbox. Add API endpoint for agent-level policy overrides. | src/app/governance/policies/ src/app/registry/[agentId]/page.tsx src/lib/db/ | M
P3 | Wave 3 | To Do | Dark Mode | No dark mode implemented despite Catalyst dark: variant classes being available — enterprise SOC/NOC users need it | Add CSS custom property overrides in :root[data-theme='dark'] in globals.css. Add theme toggle component. Leverage existing Catalyst dark: classes. | src/app/globals.css src/app/layout.tsx | L
P3 | Wave 3 | To Do | Accessibility | Only 29 ARIA attributes across 345 files — missing skip links, aria-live regions, table scope attributes, and 44px touch targets on custom buttons | Accessibility hardening pass: add skip link to layout.tsx, aria-live for chat/notifications, scope on table headers, replace custom button touch targets with Catalyst Button. | src/app/layout.tsx src/components/ui/button.tsx src/components/ui/table.tsx | M
P3 | Wave 3 | Done | Typography Line Height | Mixed /6, /7, /8 line-heights across heading scale — not aligned to 4px/8px baseline grid | Standardize all type scale line-heights to /6 or /8 increments in Catalyst heading component and any overrides. | src/components/catalyst/heading.tsx src/components/ui/heading.tsx | S | Session 119 — Wave 1 Foundation
P3 | Wave 3 | Done | Max Width Constraint | No max-width on main content area — ultra-wide monitors (2560px+) cause uncomfortable line lengths in tables and text | Add max-w-screen-2xl mx-auto to main content wrapper in layout.tsx. | src/app/layout.tsx | S | Session 119 — Wave 1 Foundation
P3 | Wave 3 | To Do | Optimistic Updates | No optimistic UI for simple mutations (status toggle, rename, inline edits) — users see loading delay for instant-feeling operations | Implement via React Query's onMutate callback for status changes and inline edits. | All mutation handlers across page components | M
P3 | Wave 3 | To Do | Policy Cascade Warning | Deleting a policy shows no impact preview — admins cannot know how many blueprints depend on the policy they are removing | Query dependent blueprint count before confirming deletion. Display count in Catalyst Dialog confirmation: 'This policy is evaluated against N blueprints.' | src/app/governance/policies/[id]/edit/page.tsx src/app/api/governance/policies/[id]/route.ts | S

## Dashboard
Intellios UX Audit — Progress Dashboard
Priority Summary |  |  |  |  | Effort Distribution
Priority | Total | To Do | In Progress | Done | Effort | Count
P0 | 5 | 1 | 0 | 4 | S (Small) | 19
P1 | 7 | 1 | 0 | 6 | M (Medium) | 15
P2 | 8 | 0 | 0 | 8 | L (Large) | 2
P3 | 6 | 3 | 0 | 3
Catalyst | 10 | 0 | 0 | 10
TOTAL | 36 | 5 | 0 | 31 | Wave Summary
[5 empty] | Wave | Items
[5 empty] | Wave 1 (1–2 wks) | 14
[5 empty] | Wave 2 (2–4 wks) | 14
[5 empty] | Wave 3 (4–6 wks) | 8
Legend
P0 | 5
P1 | 7
P2 | 8
P3 | 6
S | Small effort: < 1 day
M | Medium effort: 1–5 days
L | Large effort: 1–3 weeks